## Casey O'Rourke
Project 005 - eDocent
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
2(9/12-9/18) | Casey O'Rourke | 7.5 | 6 | 1.5 | 0 - learning Django 1 - PPP 2 - Designing program 5 - Coordinating group | 1 | 1 | 1 | 0 | 0 | 3 | 0 | 0,1,2,5 | 8
3(9/19-9/25) | Casey O'Rourke | 14.5 | 13 | 1.5 | 0 - Django 1 - SPPP 2 - Architecture 5 - Coordinating group | 4 | 5 | 1 | 0 | 0 | 3 | 0 | 2,3,4 | 10
4(9/26-10/2) | Casey O'Rourke | 10.5 | 9 | 1.5 | 0 - Django and Heroku 1 - Weekly review sheet 2 - Architecture 3 - Implementation 5 - Coordinating group | 3 | 0.5 | 2 | 2 | 0 | 1.5 | 0 | 0,1,2,3,5 | 10
5(10/3-10/9) | Casey O'Rourke | 13 | 12 | 1 | 0 - Django and Heroku 2 - Architecture 3 - Implementation 5 - Coordinating group | 4 | 0 | 2 | 5 | 0 | 1 | 0 | 0,1,2,3,4,5 | 10
6 (10/10 - 10/16) | Casey O'Rourke | 12.5 | 11 | 1.5 | 0,1,2,3,5 | 2 | 2 | 1 | 4 | 0 | 2 | 0 | 0,1,2,3,4,5 | 10
7 (10/17 - 10/23) | Casey O'Rourke | 6 | 5 | 1 | 3,5 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 3,4,5 | 10
8 (10/24-10/30) | Casey O'Rourke | 7 | 6 | 1 | 3,4,5 | 0 | 0 | 0 | 4 | 1 | 1 | 0 | 2,3,4,5 | 10
9 (10/31 - 11/6) | Casey O'Rourke | 17 | 16 | 1 | 2,3,4,5 | 0 | 0 | 2 | 8 | 4 | 2 | 0 | 3,4,5, | 16
10 (11/7 - 11/13) | Casey O'Rourke | 10 | 9 | 1 | 0,3,4,5 | 3 | 0 | 0 | 3 | 1 | 2 | 0 | 3,4,5 | 10
11 (11/14 - 11/20) | Casey O'Rourke | 11 | 10 | 1 | 3,4,5 | 0 | 0 | 0 | 6 | 2 | 2 | 0 | 3,4,5 | 10
12 (11/21 - 11/27) | Casey O'Rourke | 2.5 | 2.5 | 0 | 3,5 | 0 | 0 | 0 | 2 | 0 | 0.5 | 0 | 3,4,5 | 20
13 (11/28 - 12/3) | Casey O'Rourke | 11 | 10 | 1 | 3,4,5 | 0 | 0 | 0 | 3 | 1 | 6 | 0

## Kritika
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
2(9/12-9/18) | Kritika Balasubramanian | 5 | 3.5 | 1.5 | 0 - learning basics of android App, Getting familiar with Github 1 - Analysing end to end process of project implementation on high level using Anroid, Django, DB | 2.5 | 1 | [5 empty] | -Get familiar with Android Appln development and create a sample page -Complete Requirements and planning Analysis, documentation | 6
3(9/19-9/25) | Kritika Balasubramanian | 8 | 7 | 1 | 0 - Creation of a sample android App 1 - Proposal planning documentation 5 - Communication and learning from team members - front end android 6 - User Story | 3 | 2 |  |  |  | 1 | 1 | - Start actual implementation of front end application for Phase1. Create Acivity and fragments for customer view | 6
4(9/26-10/2) | Kritika Balasubramanian | 6 | 5 | 1 | 3- configuring required softwares for implementation of front, also started working on the front page for displaying Art works and information related to it |  |  |  | 5 |  |  |  | - complete front end for the art works page | 6
5(10/3-10/9) | Kritika Balasubramanian | 7 | 6 | 1 | 3 - Art works page for displaying the art works image and information related to the art |  |  |  | 6 |  |  |  | - Integrate with the back end and connect the front page to the database | 6
6 (10/10 - 10/16) | Kritika Balasubramanian | 9 | 8 | 1 | 1 - Implemetation and working on splash page, fetching data from the database. 6 - presentation preparation and front end documentation |  |  |  | 6 |  |  | 2 | - work on completion of splash page and start art work page, interacting with the database page | 8
7(10/16-10/23) | Kritika Balasubramanian | 10 | 8 | 2 | 1 - fetching data from the database to populate on the art work page |  |  |  | 8 |  |  |  | Integrate the art work page with the collections page | 8
8(10/24-10/30) | Kritika Balasubramanian | 10 | 8 | 2 | 1 - Integrating with the main android project and integration witht the collections page |  |  |  | 8 |  |  |  | - Add additional fields and data to the Art work page. Work on QR code. | 8
9 (10/31 - 11/6) | Kritika Balasubramanian | 10 | 7 | 3 | 3 - Worked on retrieving jpg images from the server and displaying on frontend. Worked on QR code funstionality with Chethan. Integration on Collections page and art works page. 4 - tried using Junit for testing code and errors |  |  |  | 5 | 2 |  |  | - Work on images for all museum and art pages. Also fetch more information on the Art Page. Change the look and feel for the art work page. | 8
10 (11/7 - 11/13) | Kritika Balasubramanian | 9 | 7 | 2 | 3 - collections page and Art work page to display all the relevant details and integration with the museum page |  |  |  | 7 |  |  |  | - Work on bringing in audio feature and integrating it with the art work page | 10
11 (11/14 - 11/20) | Kritika Balasubramanian | 11 | 9 | 2 | 3 - audio feature working and integration with art work page |  |  |  | 9 |  |  |  | - Completion of QR code and displaying art work page on scanning | 6
12 (11/21 - 11/27) | Kritika Balasubramanian | 10 | 8 | 2 | 3 - retrieve the art work page while scaninning the QR code in andriod |  |  |  | 8 |  |  |  | Testing, docimentation, presentation and completion of issues in the application | 10
13 (11/28 - 12/3) | Kritika Balasubramanian | 12 | 10 | 2 | 0,4 - Used a new tool called robotium for testing 6 - preparation for the demo | 2 |  |  | 2 | 6

## Chethan
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
2(9/12-9/18) | Chethan | 8.5 | 7 | 1.5 | Prototype of the front page of the Application.Implementing Museum Home page description Activity.This dislpays the museum picture,Description of the museum. -A list of various options on the home which are dynamic. | 2 | 2 | 2 | 6 | 2 | 1 |  | -Get familiar with more features of the Android Appln development -Complete Requirements and planning Analysis, documentation | 6
3(9/19-9/25) | Chethan | 8 | 7 | 1 | -Writing the reuseable fragment module and the fragment list adapter to display custom List view .-Implementing the Http client on the android side to send and receive data from the server. | 1 | 3 | 2 | 4 | 2 |  | 1 | 2,3,4 | 10
4 (9/26 -10/2) | Chethan | 8 | 7 | 1 | -working on the commmuniction between the UI Thread and the Background Worker Thread to retrieve and display data on the front end -Handlers, Broad Cast reciever on the Android platform | 2 | 4 | 3 | 8 | 1 | 1 | 1 | 2,3,4 | 12
5(10/3-10/9) | chethan | 9 | 8 | 1 | -Implemantation of main GUI thread spawning background threads -The background thread then commmunicaiting Hours,Location and name of the museum -Communication between client and server establised | 2 | 3 | 3 | 9 | 2 | 1 | 1 | 2,3,4 | 10
6 (10/10 - 10/16) | chethan | 12 |  | 1 | -Working on implementing the google map basic functionaltiy with latitude and longitude -Working on the route to Museum from current location | 1 | 2 | 3 | 8 | 2 | 1 | 1 | 2,3,4 | 14
7 (10/17 - 10/23) | chethan | 9 | 8 | 1 | -Worked on integrating the splash page and Home page of museum -Worked on contacts | 2 | 3 |  | 10 | 2 | 1 |  | 2,3,4 | 10
8(10/24-10/30) | chethan | 10 | 9 | 1 | -Added the Collecitons Page(Activity) | 2 | 3 | 3 | 10 | 2 | 2 | 1 | 2,3,4 | 10
9 (10/31 - 11/6) | Chethan | 10 | 9 | 1 | -Diplays the list of collecitons by executing an asynchronous call - Diplaying the art object name, description , owner etc in a listview | 2 | 3 | 3 | 10 | 2 | 1 | 1 | 2,3,4 | 10
10 (11/7 - 11/13) | Chethan | 10 | 9 | 1 | -Diplaying detailed view of the art object with description,Image of the art object -also integrated social auth open source library to share status on social networks | 2 | 3 | 3 | 12 | 2 | 1 | 1 | 2,3,4 | 11
11 (11/14 - 11/20) | Chethan | 11 | 9 | 2 | -Integrated the Zxing QR to scan .Invokes the applicaiton to recieve the String | 2 | 3 | 3 | 11 | 2 | 1 | 1 | 2,3,4 | 10
12 (11/21 - 11/27) | Chethan | 12 | 10 | 2 | -the output of the QR code after scanning and invoking the art page to diaplay the picture, description, and the audio about the art pbject . | 2 | 3 | 3 | 10 | 2 | 2 | 1 | 2,3,4 | 12
13 (11/28 - 12/3) | Chethan | 12 | 10 | 2 | -integrating the Android applicaiton with the robotium automation frame work. -Testing various use cases and checking for the right output | 3 | 2 | 2 | 10 | 2 | 2 | 3 | 2,3,4 | 12

## Nisreen Dahod
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
2 (9/12-9/18) | Nisreen Dahod | 5 | 3.5 | 1.5 | 0- completing an Android programming tutorial, and becoming familiar with GitHub 2- Finding a site to make mockup prototypes for the Android UI design | 3 |  | 0.5 |  |  |  |  | Create a mockup prototype for the UI of the mobile application, create a sample Android application, and finalize Android application requirements, and writing my sections of project proposal. | 7
3(9/19-9/25) | Nisreen Dahod | 7 | 6 | 1 | 0-more Android Programming tutorials 1- Writing parts of project proposal, presentation 2- creating mockup for mobile application 6- User stories | 1.5 | 2 | 1.5 |  |  |  | 1 | start implementing parts of the android application | 8
4 (9/26 - 10/2) | Nisreen Dahod | 6.5 | 4 | 1.5 | 3- downloaded and configured SDK manager and packets needed for implementation and mapped out structure and objects needed for the mobile application |  |  |  | 4 |  |  |  | create splash page for the mobile application. This will be the first page the user sees when they enter into the application | 8
5(10/3 - 10/10) | Nisreen Dahod | 5 | 4 | 1 | 3 - created splash page for mobile application |  |  |  | 4 |  |  |  | finish splash page | 8
6 (10/10 - 10/16) | Nisreen Dahod | 10.5 | 9.5 | 1 | 1-iteration 1 presentation, backend documentation, and editing the SPPP 3-connecting splash page to DB, and developing it further |  | 1.5 |  | 8 |  |  |  |  | 7
7(10/16-10/23) | Nisreen Dahod | 4 | 3 | 1 | 1- learning about JSON and parsers |  | 3 | [6 empty] | 7
8(10/24-10/30) | Nisreen Dahod | 5 | 4 | 1 | 3- dealing with GitHub problems |  |  |  | 4 |  |  |  |  | 7
9 (10/31 - 11/6) | Nisreen Dahod | 7 | 6 | 1 | 1- pivotal tracker user stories, update SPPP, and create presentation for Iteration 2 3- fixing GitHub problems and writing a new JSON parser for splash page to get data from database |  |  |  | 6 |  |  |  | 3 | 7
10 (11/7 - 11/13) | Nisreen Dahod | 10 | 9 | 1 |  |  |  |  | 9 |  |  |  | 3 | 7
11 (11/14 - 11/20) | Nisreen Dahod | 9 | 8 | 1 | 3- audio code bugs |  |  |  | 8 |  |  |  | 3 | 4
12 (11/21 - 11/27) | Nisreen Dahod | 5 | 5 | 0 | 0- research different testing softwares and techniques 3- fixing audio code bugs | 1.5 |  |  | 3.5 |  |  |  | 0,1, 3, 4 | 7
13 (11/28 - 12/3) | Nisreen Dahod | 14 | 13 | 1 | 0- learn different test softwares for android application, learn how to use Robotium, learn how to write good tests for code, 1-update pivotal tracker, update bugs on GitHub, create slides for final presentation 3-finish audio code 4- write unit tests for functionality in android application | 3 | 3 |  | 2 | 5 |  |  | 0,1,4 | 5
14 (12/4 - 12/7) | Nisreen Dahod | 6.5 | 6.5 | 0 | 0- solving some GitHub issues 1- update SPPP, Design Document, and add intructions on how to use android app 4- write some more tests | 3 | 3 |  |  | 0.5 |  |  | n/a | n/a

## Ashley Custer
Project 5 - eDocent
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
2 (9/12 - 9/18) | Ashley Custer | 4.5 | 3 | 1.5 | 3 - Django admin 1 - meeting minutes |  | 1.5 |  | 3 |  |  |  | 3 - django models and admin | 5 hours
3 (9/19 - 9/25) | Ashley Custer | 7 | 6 | 1 | 0 - django tools, 1 - deadline planning, 3 - admin models | 2 | 2 |  | 3 |  |  |  | further development of museum admin models and github protocol | 10
4 (9/26 - 10/2) | Ashley Custer | 8 | 7 | 1 | 0 - django permissions, 0 - django geo tools, 3 - implementing permissions | 4 |  |  | 3 |  |  |  | final implementation of user permissions, implementation of museum information form field | 10
5 (10/3 - 10/9) | Ashley Custer | 10 | 9 | 1 | 0 - django permissions, 0 - django geo tools, 3 - implementing permissions | 4 |  | 5 |  |  | 1 |  | working on presentation, getting demo together, making admin more user-friendly | 8
6 (10/10 - 10/16) | Ashley Custer | 7 | 6 | 1 | 0 - learning djano permissions, 0 - learning heroku webserver, 2 - planning web interface set up, 5 - team meetings, communicating on user permissions | 2 |  | 1 |  |  | 3 |  | finalizing permissions, making admin forms more user friendly, setting up registration page | 10
7 (10/17 - 10/23) | Ashley Custer | 9 | 8 | 1 | 0.2.5. | 2 |  | 4 |  |  | 3 |  | implement new admin design
8 (10/24 - 10/30) | Ashley Custer | 5 | 4 | 1 | 0.2.5. | 2 |  | 4 |  |  | 3 |  | implement new admin design, prepare for iteration 2 deadline | 10
9 (10/31 - 11/6) | Ashley Custer | 8 | 7 | 1 | 0.3.5 | 1 |  | 6 |  |  | 1 |  | finish qr code testing | 10
10 (11/7 - 11/13) | Ashley Custer | 12 | 11 | 1 | 2-designing QR code print page, 3-implementing QR code print page, 5- group communication |  |  | 5 | 6 |  | 1 |  | finish implementing QR print page for museum users | 10
11 (11/14 - 11/20) | Ashley Custer | 10 | 9 | 1 | 3 - implement admin filtering , 4 - test filters, 5 - communication |  |  |  | 5 | 3 | 2 |  | testing, finalization, documentation | 10
12 (11/21 - 11/27) | Ashley Custer | 3 | 0 | 3 | 5- communication, 6 - documentation | [5 empty] | 1 | 2 | documentation, complete presentation | 11
13 (11/28 - 12/3) | Ashley Custer | 12 | 10 | 2 | 1 - req. analysis, 5 - meetings, 6 - presentation | 2 |  |  |  |  | 2 | 8 | n/a - project complete! | 0

## Sukaynah
Project xxx - Your Project Name
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1
2 | Sukaynah | 3.5 | 2 | 1.5 | - Reviewing Python and Java Languages - Exploring MoMa App to get a general idea - Writing in the PPP doc | 2 | [6 empty] | - Analyzing Requirment - Starting sketching the program | 6
3 | Sukaynah | 10 | 9 | 1 | - Installing Django and Django-REST framework and writing my first program - Learning more about the structure of Django and the format it sends to the web browser - Learning how to use GitHub / PivotalTracker, and creating accounts - Completing the SPPP document and the first project presentation - Writing the user stories | 5 | 2.5 (SPPP doc) 0.5 (presentation) 1 (user stories) | [5 empty] | - Programming using Django template - Mabe start woring in Django-REST framework | 8
4 | Sukaynah | 6 | 5 | 1 | - Learning more in GitHub - Familiarizing in PivotTracker - installing Django-extention & Django-GraphViz & some other necessary frameworks for building DB for the Backend - learning how to use the above frameworks - structuring the ER-diagram for the database we are going to use - Picking a user story to implement, and describing it in detail (assigning tasks and possible test) | 3 | 1 (user stories in detail) | 1 Database structuring |  |  |  |  | - learning GeoCoorDjango framework - implementing the user story - programming in the backend | 7
5(10/3-10/9) | Sukaynah | 7 | 6 | 1 | - Learning pushing to repository in github - Learning about Heroku, and using it in dealing with database - Analizing the database, adding new features and creating more links (via foriegn keys) - Working on users and addmissions (controlling the accesssing and editing) - Implementing the designed database - Going over the other team code (java) | 2 (github) 2 (Heroku) | 1 | 0.5 | 0.5 |  |  |  | - Completing the admin by adding more features - Modifying the database to allow more featured field (for example, using coordinate type instead of character field for the location of the museum) | 8
6 (10/10 - 10/16) | Sukaynah | 7.5 | 6.5 | 1 | - Learning how to allow the application register users (a user for each museum) - Applying the method by adding new directories and modifying the necessary files - Pushing the designed code to github - Writing in the SPPP2 document - Preparing for the iteration1 presentation (database modeling part) - Writing the main points in the project documentations | 1 | 0.5 (database modeling) |  | 3 (registration feature) |  |  | 2 (SPPP2, presentation, and documentations) | - Improving the database by modifying some fields types - Restricting the access of each user only to his info - Inhancing security | 5
7 (10/16 - 10/23)?
8 (10/24 - 10/30)
9 (10/31 - 11/6) | Sukaynah | 12.25 | 12.25 | 0 | - Preparing for the presentation for iteration2 - Adding the registration feature (installing dijango-registration-redux framework & modifying the custom registration folder) |  |  |  | 12 (registration related code) |  |  | 0.25 (presentation) | - Enhancing the registration feature (more convenient) | 8
10 (11/7 - 11/13) | Sukaynah | 7 | 7 | 0 | - Searching the web to find how regisration can be improved - Doing the assignment uploaded in blackboard and reading the related material in textbook and lecture slides | 1 (searching) | [5 empty] | 6 | - Enhancing the registration feature (more convenient) | 8
11 (11/14 - 11/20) | Sukaynah | 4.5 | 4.5 | 0 | - Working to solve the error in custom registration | [6 empty] | 4.5 | - Getting custom registration work - Final presentation related work | 6
12 (11/21 - 11/27) | Sukaynah | 5 | 5 | 0 | - answering the review exercise # 2 questions, and reviewing the related material I missed - Still working on the custom registration - preparing for the inall presentation | 3 (exercises#2) | [5 empty] | 0.5 (presentation) 1.5 (custom registration) | - Getting custom registration work - Final presentation related work | 8
13 (11/28 - 12/4) | Sukaynah | 13 | 12 | 1 | - Final presentation preparation (use case diagram & update the er-diagram) - Finally, solving the error and getting the registration work - Allowing the user to reset the password in case he forgot it - Updating the documentation |  | 3 (diagrams) |  | 6 (registration) 2 (password) |  |  | 1 (documentations) | - Finishing up the whole project, including its requirment - Studying for the final | 10